## Template
Project Communications Plan Project: Date and Version:
Communications Item | Item Owner | Target Audience | Media/Channels | Frequency | Purpose/Objective | Comments
Kick-off Meeting | Project Manager | Project Team, Key Stakeholders | In-person / Video Conference | One-time | Introduce project, align on goals | Essential for alignment and clarity
Weekly Status Report | Project Manager | Internal Team, Sponsor | Email / Shared Dashboard | Weekly | Provide updates on progress and risks | Use to identify roadblocks early
Design Review Meetings | Web Developer | Marketing Lead, IT Manager | Video Conference | Bi-weekly | Gather feedback on design elements | Ensure alignment with project vision
User Acceptance Testing (UAT) | IT Manager | Selected End Users | In-person / Virtual | Once per phase | Validate functionality and gather user feedback | Critical for identifying issues before launch
Training Sessions | HR Manager | Internal Staff | In-person / Video Conference | As needed | Train staff on new website features and CMS | Ensure all staff are comfortable with changes
Customer Feedback Collection | Sales Team Lead | End Users/Customers | Online Survey | Monthly | Gather user input for continuous improvement | Use incentives to boost participation
Executive Status Reports | Project Manager | Executive Leadership | Email / Presentation | Monthly | Provide updates on project status and budget | Highlight successes and challenges
Social Media Announcements | Marketing Lead | General Public | Social Media Platforms | As needed | Promote website features and engage users | Use visuals and clear calls to action
Risk Management Meetings | Project Manager | Core Project Team | Video Conference | Monthly | Review and manage project risks | Ensure proactive risk mitigation strategies
Post-Launch Review | Project Manager | All Stakeholders | Video Conference | One-time | Evaluate project success and areas for improvement | Collect feedback for future projects

## Instructions
Category | Instructions
Introduction | List project name, date, and version
Communications Item | Define the communication item. For example: Status Reports, Change Control Meeting
Item Owner | Identify the individual responsible for the Communications Item
Target Audience | Identify stakeholders who are impacted by the Communications Item
Media Channels | Describe the media that will be used to support the communications Item. For example: E-Mail, Teams Meeting, Slack
Frequency | Define when and how often the Communications Item will be addressed
Purpose Objective | Define the purpose and value of the Communications Item
Comments | Provide any clarifying comments or links to key references

## Example
Project Communications Plan Project: Project ABC Date and Version: 1 February 20xx, Version 1
Communications Item | Item Owner | Target Audience | Media/Channels | Frequency | Purpose/Objective | Comments
Kick-off Meeting | Project Manager | Project Team, Key Stakeholders | In-person / Video Conference | One-time | Introduce project, align on goals | Essential for alignment and clarity
Weekly Status Report | Project Manager | Internal Team, Sponsor | Email / Shared Dashboard | Weekly | Provide updates on progress and risks | Use to identify roadblocks early
Email Update to Stakeholders | Project Coordinator | Stakeholders, External Partners | Email | Bi-weekly | Keep stakeholders informed of progress | Use a consistent format for updates
Final Project Review Presentation | Team Lead | Leadership and External Stakeholders | Webinar / In-Person Presentation | One-time | Present outcomes and gather feedback | Capture lessons learned for future use