## Risk Register Template
Project: Date:
# | Cause (Condition/Situation) | Event | Impact | Risk Owner | Category | Probability Risk Rating | Impact Risk Rating | Risk Score | Trigger | Response
1 | Lack of Management Support | Project delays due to insufficient resources | Increased costs and missed deadlines | Project Manager | Organizational | 4 | 5 | 20 | Lack of executive engagement | Schedule regular check-ins with leadership.
2 | Technical Integration Challenges | Failure of system integration | Loss of functionality, increased costs | IT Manager | Technical | 3 | 4 | 12 | Integration testing failures | Develop a detailed integration plan with contingency steps.
3 | Inadequate User Training | Users struggle to adopt the new system | Decreased productivity, poor user experience | HR Manager | Operational | 4 | 5 | 20 | Low user feedback scores | Implement comprehensive training sessions and materials.
4 | Insufficient Testing | Undetected bugs in the system | Delayed launch, increased costs | IT Manager | Technical | 3 | 4 | 12 | High number of post-launch issues | Schedule multiple testing phases and user feedback loops.
5 | Delays in Content Delivery | Incomplete website at launch | Poor launch quality, negative user perception | Marketing Lead | Schedule | 3 | 4 | 12 | Content not finalized on time | Establish clear content deadlines and accountability.
6 | Market Competition | Lower user engagement post-launch | Reduced market share, decreased revenue | Marketing Lead | Market-related | 3 | 5 | 15 | Increased competitor activity | Monitor market trends and adjust strategies accordingly.
7 | Budget Overruns | Exceeding project budget | Financial strain, project scope reduction | Finance Manager | Financial | 2 | 4 | 8 | Budget review discrepancies | Regular budget monitoring and adjustment strategies.
Total Risk Score | [8 empty] | Risk Exposure
|  | Probability Risk Rating |  | Impact Risk Rating
|  | 5: High |  | 5: High
|  | 4: High to Moderate |  | 4: High to Moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to Low |  | 2: Moderate to Low
|  | 1: Low |  | 1: Low

## Instructions
Explanation of Columns: Risk #: Unique identifier for the risk. Cause: The root cause or condition driving the risk. Event: Description of the risk event. Impact: The consequence or impact of the risk event. Risk Owner: The person responsible for managing the risk. Category: The type or category of the risk (e.g., Schedule, Technical, Operational, Legal, Financial). Probability: The likelihood of the risk occurring (1-5). Impact: The severity of the risk's impact (1-5). Threats are scored as a positive number. Opportunities are scored as a negative number. Risk Score: A score representing the combined effect of probability and impact. Trigger: The indicator or event that signifies the risk is occurring. Response: The planned action to mitigate or capitalize on the risk. Risk Exposure: The sum of all risk scores. Threats increase the total risk score. Opportunities reduce the overall risk score.

## Risk Register Example
Project: Off Site Date: June 19 20XX
# | Cause (Condition/Situation) | Event | Impact | Risk Owner | Category | Probability Risk Rating | Impact Risk Rating | Risk Score | Trigger | Response
1 | Management Support | 1. Great Event 2. Super Turnout | Increased motivation | Bill Martin | O | 5 | -5 | -25 | High RSVP | 1. Market 2. Prizes
4 | Catering | Late Food Delivery | Delayed events | Food Services | T | 3.5 | 5 | 17.5 | None | Call 1-Day Prior
3 | Multiple Projects | Lack of capacity | Schedule delays | Bill Martin | T | 4 | 4 | 16 | Missed deadlines | Use Staffing Mgt Plan
2 | Bad Weather | 1. Reduced Turnout 2. Late Start | Reduced impact | Sanya Kumar | T | 3 | 4 | 12 | Weather Report | Ensure inside venue Plan B
Total Risk Score | [7 empty] | 20.5 | Risk Exposure
May use the Project Risk Score: Total Negative scores - positive scores. Larger the gap--the more risk the project has.
|  | Probability Risk Rating |  | Impact Risk Rating
|  | 5: High |  | 5: High
|  | 4: High to Moderate |  | 4: High to Moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to Low |  | 2: Moderate to Low
|  | 1: Low |  | 1: Low